## Website
Women's Wellness Center (HRMC)
HS Project Task Track |  |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May
Women's Wellness Center (HRMC) Review |  |  |  |  | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
[5 empty] | Q1 2018 | [12 empty] | Q2 2018
| RESPONSIBLE | START DATE | DUE DATE | ACTUAL DATE
DISCOVERY
HS/HRMC discovery call | HS | COMPLETED | bar: January 1 to January 8
HRMC to provide online intake form | HRMC | 2018-01-10 | 2018-01-15 | bar: January 8 to January 15
Practice Brochure
HS to provide brochure copy and art | HS | 2018-01-10 | 2018-01-31 | bar: January 8 to January 29
HRMC to provide feedback or approval | HRMC | 2018-01-31 | 2018-02-07 | bar: January 29 to February 5
Inserts (4)
HS to provide insert copy and art | HS | 2018-01-10 | 2018-01-31 | bar: January 8 to January 29
HRMC to provide feedback or approval | HRMC | 2018-01-31 | 2018-02-07 | bar: January 29 to February 5
Folder
HS to provide folder copy and art | HS | 2018-01-10 | 2018-01-31 | bar: January 8 to January 29
HRMC to provide feedback or approval | HRMC | 2018-01-31 | 2018-02-07 | bar: January 29 to February 5
Landing Page
HS to provide landing page copy | HS | 2018-01-10 | 2018-01-26 | bar: January 8 to January 22
HRMC to provide feedback or approval of copy | HRMC | 2018-01-26 | 2018-01-31 | bar: January 22 to January 29
HS to provide designed landing page | HS | 2018-01-31 | 2018-02-07 | bar: January 29 to February 5
HRMC to provide feedback or approval of landing page | HRMC | 2018-02-07 | 2018-02-09 | bar: February 5
Website
HS to provide home page comp and site map | HS | 2018-01-10 | 2018-01-31 | bar: January 8 to January 29
HRMC to provide feedback or approval of home page comp and site map | HRMC | 2018-01-31 | 2018-02-07 | bar: January 29 to February 5
HS to provide full website copy | HS | 2018-02-07 | 2018-02-28 | bar: February 5 to February 26
HRMC to provide feedback or approval of copy | HRMC | 2018-02-28 | 2018-03-07 | bar: February 26 to March 5
HS to provide full development site | HS | 2018-03-07 | 2018-03-30 | bar: March 5 to March 26
HRMC to provide feedback or approval of website | HRMC | 2018-03-30 | 2018-04-06 | bar: March 26 to April 2